## Main
Scrum Project |  |  | Product Status
Sponsor
Product | RMS
Active versions | 1
|  |  | Product Owner | CMU. Duy Tan University
Team |  |  | Project Champion
Scrum Master | Hoàng Nghĩa Khuê |  | Other Stakeholders
Developers | Hoàng Nghĩa Khuê
Phan Minh Phú
Huỳnh Việt Trí
Phạm Hưng Đạt
Nguyễn Ngọc Thành
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks
1 | Start up | 2021-05-13 | 2021-05-16 | Done |  | 1.1 | 2021-05-17 | 2021-05-26 | Done | 53 | 53
1.1 | Gathering Requirement | 2021-05-13 | 2021-05-13 | Done |  | 1.2 | 2021-05-19 | 2021-05-21 | Done | 16 | 16
1.2 | Create Proposal Document | 2021-05-14 | 2021-05-14 | Done |  | 1.3 | 2021-05-19 | 2021-05-24 | Done | 11 | 11
1.3 | Project Kick-off Meeting | 2021-05-15 | 2021-05-15 | Done |  | 1.4 | 2021-05-20 | 2021-05-25 | Done | 9 | 10
1.4 | Make Project Plan Document | 2021-05-16 | 2021-05-16 | Done |  | 1.5 | 2021-05-22 | 2021-05-23 | Done | 9 | 9
2 | Development | 2021-05-17 | 2021-06-22 | Done |  | 1.6 | 2021-05-20 | 2021-05-25 | Done | 9 | 10
2.1 | Sprint 1 | 2021-05-17 | 2021-05-28 | Done |  | 1.7 | 2021-05-21 | 2021-05-25 | Done | 9 | 9
2.2 | Sprint 2 | 2021-05-29 | 2021-06-09 | Done |  | 2.1 | 2021-05-29 | 2021-06-03 | Done | 8 | 8
2.3 | Sprint 3 | 2021-06-10 | 2021-06-22 | Done |  | 2.2 | 2021-05-29 | 2021-05-29 | Done | 16 | 16
3 | Project’s Meeting | 2021-06-23 | 2021-06-23 | Done |  | 2.3 | 2021-05-29 | 2021-05-29 | Done | 13 | 13
4 | Final Release | 2021-06-24 | 2021-06-24 | Done |  | 2.4 | 2021-05-29 | 2021-06-01 | Done | 18 | 18
[6 empty] | 2.5 | 2021-05-29 | 2021-05-29 | Done | 13 | 13
[6 empty] | 2.6 | 2021-05-30 | 2021-06-05 | Done | 13 | 13
[6 empty] | 2.7 | 2021-05-29 | 2021-05-29 | Done | 8 | 8
[6 empty] | 2.8 | 2021-06-02 | 2021-06-05 | Done | 14 | 14
[6 empty] | 3.1 | 2021-06-10 | 2021-06-22 | Done | 15 | 15
[6 empty] | 3.2 | 2021-06-12 | 2021-06-20 | Done | 8 | 8
[6 empty] | 3.3 | 2021-06-10 | 2021-06-19 | Done | 12 | 12
[6 empty] | 3.4 | 2021-06-12 | 2021-06-22 | Done | 12 | 12
[6 empty] | 3.5 | 2021-06-11 | 2021-06-22 | Done | 12 | 12
[6 empty] | 3.6 | 2021-06-11 | 2021-06-22 | Done | 28 | 28
[6 empty] | 3.7 | 2021-06-10 | 2021-06-20 | Done | 16 | 16
[6 empty] | 3.8 | 2021-06-11 | 2021-06-22 | Done | 16 | 16
[6 empty] | 3.9 | 2021-06-11 | 2021-06-22 | Done | 16 | 16

## Backlog
Backlog
Id | Epics | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
PB00 | API Server | Manager | Have my app working on more platform in the future | I can reach more customers. | Each role have it own permissions to access API |  | 4 | In process
PB01 | Login | Manager | Login into the system | I can manager list of dishes, monitor invoices. | Using email and password to login Email is required Password is required |  | 3 | Done
|  | Cashier | Login into the system | I can select table, select dish and order for customer. I can view invoice information and print it. | Using email and password to login Email is required Password is required |  | 3 | Done
PB02 | Logout | Manager | Get out of my account when i complete my work | No one can't do anything bad with my account. | Must be login first to logout The api_token must be empty (null) after login |  | 2 | Done
|  | Cashier | Get out of my account | Another cashier can use it. | Must be login first to logout The api_token must be empty (null) after login |  | 2 | Done
PB03 | Create dish | Manager | Add new dish into the menu | Everyone can see and order it. | The dish must be not existed Dish name is required Price must be a number (double) Description is optional |  | 2 | In process
PB04 | View dish | Manager | View dish information | I can see if the dish information is correct or not, is it need to update or not. | The dish must be existed. |  | 2 | In process
PB05 | Update dish | Manager | Update dish information | The dish information will correct and uptodate. | The dish must be not existed Dish name is required Price must be a number (double) Description is optional |  | 2 | In process
PB06 | Delete dish | Manager | Remove dish from the menu | The no longer exist dish will not be appear. | The dish must be existed. |  | 2 | In process
PB07 | Monitor invoices | Manager | Monitor, filter, see today / month / year invoices | I can manager my restaurant more effecitve. | Monitor by day / month / year. |  | 1 | In process
PB08 | Homepage | Customer | Have a easy to use homepage interface | I can know what i should do and find what i want to do easily. |  |  | 2
PB09 | Select table | Cashier | Choose table for customer | They can sit and eat. | Table must be existed and empty to be selected. Can select table by enter code or scan a QR code. |  | 3
|  | Customer | Have a table | I can sit and eat. |  |  | 3
PB10 | Select dish | Cashier | Select dish for customer | The customer can have what they want to eat. | Must display necessary information (name, price, description) After select, display to a list Can add, subtract items amount at a list |  | 3
|  | Customer | See dish information | I can decide what i want to eat. | Must display necessary information (name, price, description) After select, display to a list Can add, subtract items amount at a list |  | 3
PB11 | Order dish | Cashier | Order dish for customer | They can have the food they want to eat. | Number of dishes must be >= 1 |  | 3
|  | Customer | Order dish | I have something to eat. |  |  | 3
PB12 | View invoice | Cashier | See customer invoice information | Tell them, see what they are eating |  |  | 2
|  | Customer | See my invoice information | Prepare money and decide to keep eat or stop |  |  | 1
PB13 | Print invoice | Cashier | Print customer invoice | The customer can see it or the waiter can bring it to the customer |  |  | 1

## Sprint Task
Sprint Task
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | PB00 | Analysis & Design database | Phan Minh Phu | Done | 10 | 10 | 0 | 8 | 2
1.1 | PB00 | Code database | Phan Minh Phu | Done | 10 | 10 | 0 | 4 |  | 6
1.1 | PB00 | Test database | Phan Minh Phu | Done | 5 | 5 | 0 |  |  | 5
1.1 | PB00 | Create PHP server | Phan Minh Phu | Done | 5 | 5 | 0 |  | 5
1.1 | PB00 | Code API for Login. Logout | Phan Minh Phu | Done | 6 | 6 | 0 |  | 2 |  | 2 |  | 2
1.1 | PB00 | Code API for Dish Management | Phan Minh Phu | Done | 10 | 10 | 0 |  |  |  | 2 |  | 4 | 4
1.1 | PB00 | Test API server | Phan Minh Phu | Done | 5 | 5 | 0 | [5 empty] | 1 | 4
1.1 | PB00 | Deploy API server | Phan Minh Phu | Done | 2 | 2 | 0 | [6 empty] | 2
1.2 | PB01 | Design Login UI | Hoang Nghia Khue | Done | 3 | 3 | 0 |  |  | 3
1.2 | PB01 | Code Login UI | Phan Minh Phu | Done | 5 | 5 | 0 |  |  |  | 5
1.2 | PB01 | Code Login & Test | Phan Minh Phu | Done | 8 | 8 | 0 |  |  |  |  | 8
1.3 | PB02 | Design Logout UI | Hoang Nghia Khue | Done | 3 | 3 | 0 |  |  | 3
1.3 | PB02 | Code Logout UI | Phan Minh Phu | Done | 3 | 3 | 0 |  |  |  |  | 3
1.3 | PB02 | Code Logout & Test | Phan Minh Phu | Done | 5 | 5 | 0 |  |  |  |  | 5
1.4 | PB03 | Design Create dish | Hoang Nghia Khue | Done | 3 | 3 | 0 |  |  | 2 | 1
1.4 | PB03 | Code Create dish UI | Nguyen Ngoc Thanh | Done | 1 | 1 | 0 | [5 empty] | 1
1.4 | PB03 | Code Create dish & Test | Nguyen Ngoc Thanh | Done | 5 | 6 | 0 | [6 empty] | 3 | 3
1.5 | PB04 | Design View dish UI | Hoang Nghia Khue | Done | 3 | 3 | 0 |  |  |  | 3
1.5 | PB04 | Code View dish UI | Nguyen Ngoc Thanh | Done | 1 | 1 | 0 | [5 empty] | 1
1.5 | PB04 | Code View dish & Test | Nguyen Ngoc Thanh | Done | 5 | 5 | 0 | [6 empty] | 5
1.6 | PB05 | Design Update dish | Hoang Nghia Khue | Done | 3 | 3 | 0 |  |  |  | 3
1.6 | PB05 | Code Update dish UI | Nguyen Ngoc Thanh | Done | 1 | 1 | 0 | [6 empty] | 1
1.6 | PB05 | Code Update dish & Test | Nguyen Ngoc Thanh | Done | 5 | 6 | 0 | [7 empty] | 3 | 3
1.7 | PB06 | Design Delete dish UI | Hoang Nghia Khue | Done | 3 | 3 | 0 |  |  |  |  | 3
1.7 | PB06 | Code Delete dish UI | Nguyen Ngoc Thanh | Done | 1 | 1 | 0 | [6 empty] | 1
1.7 | PB06 | Code Delete dish & Test | Nguyen Ngoc Thanh | Done | 5 | 5 | 0 | [7 empty] | 2 | 3
2.1 | PB00 | Code API | Phan Minh Phu | Done | 8 | 8 | 0 | 2 | 2 |  | 2 |  | 2
2.2 | PB08 | Design Web homepage UI | Huynh Viet Tri | Done | 8 | 8 | 0 |  |  |  | 1 |  | 2 | 3 |  | 2
2.2 | PB08 | Code Web homepage UI | Huynh Viet Tri | Done | 8 | 8 | 0 |  |  |  |  | 2 |  | 2 | 2 | 2
2.3 | PB09 | Design Web select table UI | Pham Hung Dat | Done | 5 | 5 | 0 |  |  | 2 | 2 | 1
2.3 | PB09 | Code Web select table UI | Pham Hung Dat | Done | 8 | 8 | 0 |  |  |  | 2 | 2 | 2 | 2
2.4 | PB09 | Design Cashier select table UI | Nguyen Ngoc Thanh | Done | 5 | 5 | 0 | 4 | 1
2.4 | PB09 | Code Cashier select table UI | Nguyen Ngoc Thanh | Done | 5 | 5 | 0 | 2 | 3
2.4 | PB09 | Code Cashier select table & Test | Nguyen Ngoc Thanh | Done | 8 | 8 | 0 |  | 3 | 2 | 3
2.5 | PB10 | Design Web select dish UI | Hoang Nghia Khue | Done | 5 | 5 | 0 |  | 2 |  | 3
2.5 | PB10 | Code Web select dish UI | Hoang Nghia Khue | Done | 8 | 8 | 0 | 3 |  | 2 | 3
2.6 | PB10 | Design Cashier select dish UI | Phan Minh Phu | Done | 3 | 3 | 0 |  | 1 | 2
2.6 | PB10 | Code Cashier select dish UI | Phan Minh Phu | Done | 5 | 5 | 0 |  |  | 3 | 2
2.6 | PB10 | Code Cashier select dish & Test | Phan Minh Phu | Done | 5 | 5 | 0 |  |  |  | 2 | 3
2.7 | PB11 | Design Web order dish UI | Hoang Nghia Khue | Done | 3 | 3 | 0 | [6 empty] | 3
2.7 | PB11 | Code Web order dish UI | Hoang Nghia Khue | Done | 5 | 5 | 0 | [5 empty] | 2 |  | 3
2.8 | PB11 | Design Cashier order dish UI | Phan Minh Phu | Done | 3 | 3 | 0 |  |  |  |  | 3
2.8 | PB11 | Code Cashier order dish UI | Phan Minh Phu | Done | 3 | 3 | 0 |  |  |  |  | 1 | 2
2.8 | PB11 | Code Cashier order dish & Test | Phan Minh Phu | Done | 8 | 8 | 0 |  |  |  |  | 1 | 2 | 4 | 1
3.1 | PB00 | Code API | Phan Minh Phu | Done | 15 | 15 | 0 | 2 | 1 | 2 | 3 | 1 | 3 | 1 | 2
3.2 | PB08 | Code Web homepage & Test | Huynh Viet Tri | Done | 8 | 8 | 0 |  |  | 3 |  | 2 | 3
3.3 | PB09 | Code Web select table & Test | Pham Hung Dat | Done | 12 | 12 | 0 | 1 | 3 | 4 | 2 | 2
3.4 | PB10 | Code Web select dish & Test | Hoang Nghia Khue | Done | 12 | 12 | 0 |  |  | 2 | 2 | 2 | 1 | 2 | 3
3.5 | PB11 | Code Web order dish & Test | Hoang Nghia Khue | Done | 12 | 12 | 0 |  | 3 |  | 2 | 2 |  | 3 | 2
3.6 | PB12 | Design Web view invoice UI | Huynh Viet Tri | Done | 8 | 8 | 0 |  | 2 | 2 |  | 2 |  | 2
3.6 | PB12 | Code Web view invoice UI | Pham Hung Dat | Done | 8 | 8 | 0 |  | 4 |  |  | 2 | 2
3.6 | PB12 | Code Web view invoice & Test | Hoang Nghia Khue | Done | 12 | 12 | 0 |  | 1 | 2 | 2 |  | 3 | 4
3.7 | PB12 | Design Cashier view invoice UI | Phan Minh Phu | Done | 5 | 5 | 0 | 2 | 2 | 1
3.7 | PB12 | Code Cashier view invoice UI | Phan Minh Phu | Done | 3 | 3 | 0 |  | 2 | 1
3.7 | PB12 | Code Cashier view invoice & Test | Phan Minh Phu | Done | 8 | 8 | 0 |  |  | 2 | 2 | 3 | 1
3.8 | PB13 | Design Print invoice UI | Nguyen Ngoc Thanh | Done | 5 | 5 | 0 |  | 2 | 3
3.8 | PB13 | Code Print invoice UI | Nguyen Ngoc Thanh | Done | 8 | 9 | 0 |  | 2 | 2 |  | 1 |  | 1 | 3
3.8 | PB13 | Code Print invoice & Test | Nguyen Ngoc Thanh | Done | 3 | 3 | 0 |  |  | 1 | 1 |  | 1
3.8 | PB14 | Design Monitor invoices UI | Huynh Viet Tri | Done | 5 | 5 | 0 |  | 1 | 2 | 2
3.9 | PB14 | Code Monitor invoices UI | Huynh Viet Tri | Done | 3 | 3 | 0 |  | 2 |  |  |  | 1
3.9 | PB14 | Code Monitor invoices & Test | Huynh Viet Tri | Done | 8 | 8 | 0 |  |  |  | 2 | 1 |  | 3 | 2
|  |  |  | Total | 314 | 316 | 0 | 28 | 39 | 47 | 47 | 45 | 33 | 46 | 21 | 10 | 0
|  |  |  | Burn down |  |  |  | 286 | 247 | 200 | 153 | 108 | 75 | 29 | 8 | -2 | -2
|  |  |  | Burn up |  |  |  | 28 | 67 | 114 | 161 | 206 | 239 | 285 | 306 | 316 | 316

## Retrospective
Retrospective Log |  |  |  | Start Doing | Stop Doing | Remarks
Sprint # | Date | Owner | Continue Doing

## Impediment
Impediments |  | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks
Id | Description

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Default status for items | https://www.yodiz.com/help/default-status-for-items